## Sprint 2-4 Backlog
Sprint No. | Story ID | Task ID | Task Description | Task Story Points | Dependencies | Deliverables
2 | AQ-301 | AQ-301-T1 | Validate predecessor parsing and INIT-node handling | 3 | None | Stable predecessor/INIT interpretation rules
2 | AQ-301 | AQ-301-T2 | Verify sequential and parallel lead-time calculations | 2 | AQ-301-T1 | Correct lead-time calculation logic
2 | AQ-301 | AQ-301-T3 | Validate critical-path logic for material-output endpoints | 2 | AQ-301-T2 | Accurate critical-path selection
2 | AQ-301 | AQ-301-T4 | Handle duplicate, missing, and malformed activity references | 2 | AQ-301-T1 | Robust input-validation behavior
2 | AQ-301 | AQ-301-T5 | Review node and edge labels plus DOT output quality | 2 | AQ-301-T2, AQ-301-T3 | Cleaner process diagram output
2 | AQ-302 | AQ-302-T1 | Validate role extraction from questionnaire data | 2 | None | Reliable role extraction logic
2 | AQ-302 | AQ-302-T2 | Verify owner-to-owner handoff mapping logic | 2 | AQ-302-T1 | Accurate people handoff mapping
2 | AQ-302 | AQ-302-T3 | Validate automation/manual coloring and labeling rules | 2 | AQ-302-T2 | Correct visual semantics in people diagram
2 | AQ-302 | AQ-302-T4 | Handle duplicate roles, empty owners, and self-loop cases | 2 | AQ-302-T1 | Hardened people-diagram edge cases
2 | AQ-303 | AQ-303-T1 | Validate automation tool extraction and normalization | 2 | None | Clean tool inventory for diagraming
2 | AQ-303 | AQ-303-T2 | Verify same-tool and cross-tool dependency mapping | 2 | AQ-303-T1 | Accurate technology flow mapping
2 | AQ-303 | AQ-303-T3 | Improve edge deduplication and aggregated edge labeling | 2 | AQ-303-T2 | Reduced duplicate edges in technology diagram
2 | AQ-303 | AQ-303-T4 | Handle missing tools, aliases, and invalid tool-pair relationships | 2 | AQ-303-T1 | More resilient technology diagram generation
2 | AQ-304 | AQ-304-T1 | Align DOT, Mermaid, and PlantUML generation behavior | 2 | AQ-301, AQ-302, AQ-303 | Consistent multi-format diagram outputs
2 | AQ-304 | AQ-304-T2 | Standardize PNG rendering and export output checks | 2 | AQ-304-T1 | Reliable rendered diagram artifacts
2 | AQ-304 | AQ-304-T3 | Validate download naming and artifact directory structure | 1 | AQ-304-T2 | Standardized artifact naming/location
2 | AQ-304 | AQ-304-T4 | Confirm reviewer-friendly consistency across architecture types | 1 | AQ-304-T1 | Consistent user-facing output set
2 | AQ-305 | AQ-305-T1 | Standardize titles, headers, and metadata in exports | 2 | AQ-304-T1 | Uniform export metadata
2 | AQ-305 | AQ-305-T2 | Improve formatting for lists, sections, and grouping | 1 | AQ-305-T1 | Better document readability
2 | AQ-305 | AQ-305-T3 | Validate narrative alignment with generated architecture type | 1 | AQ-305-T1 | Correct narrative-to-diagram alignment
2 | AQ-305 | AQ-305-T4 | Verify file naming, versioning, and MIME/download behavior | 1 | AQ-305-T1 | Download-ready export package
3 | AQ-201 | AQ-201-T1 | Validate required questionnaire columns and sheet assumptions | 2 | None | Ingestion input contract
3 | AQ-201 | AQ-201-T2 | Improve malformed and incomplete Excel failure handling | 2 | AQ-201-T1 | Better ingestion error handling
3 | AQ-201 | AQ-201-T3 | Strengthen parsing for xlsm, xlsx, docx, pdf, and txt inputs | 2 | AQ-201-T1 | Multi-format ingestion support
3 | AQ-201 | AQ-201-T4 | Normalize extracted text and metadata before chunking | 2 | AQ-201-T3 | Clean normalized ingestion payloads
3 | AQ-201 | AQ-201-T5 | Ensure bad files are skipped without breaking the session | 1 | AQ-201-T2, AQ-201-T3 | Session-safe ingestion behavior
3 | AQ-202 | AQ-202-T1 | Review chunk size and overlap strategy across sources | 2 | AQ-201-T4 | Improved chunking configuration
3 | AQ-202 | AQ-202-T2 | Reduce redundant and low-value chunks | 2 | AQ-202-T1 | Higher-value retrieval corpus
3 | AQ-202 | AQ-202-T3 | Improve chunk boundary quality for coherent retrieval | 1 | AQ-202-T1 | Better semantic chunk integrity
3 | AQ-202 | AQ-202-T4 | Preserve source attribution and traceability in chunks | 1 | AQ-202-T2 | Source-aware retrieval metadata
3 | AQ-203 | AQ-203-T1 | Validate node creation for pillars, roles, tools, and activities | 2 | AQ-201-T4 | Complete knowledge graph node model
3 | AQ-203 | AQ-203-T2 | Verify relationship mapping across core graph edges | 2 | AQ-203-T1 | Correct graph relationships
3 | AQ-203 | AQ-203-T3 | Handle partial or missing questionnaire data during graph build | 2 | AQ-203-T1 | Resilient graph build process
3 | AQ-203 | AQ-203-T4 | Validate graph persistence, reload, and integrity checks | 2 | AQ-203-T2 | Persisted and reloadable graph store
3 | AQ-204 | AQ-204-T1 | Refine intent-based retrieval filtering by discipline | 2 | AQ-202, AQ-203 | Better query-to-context routing
3 | AQ-204 | AQ-204-T2 | Improve ranking for People, Process, and Technology queries | 2 | AQ-204-T1 | Better relevance ordering
3 | AQ-204 | AQ-204-T3 | Tune graph and vector retrieval balance to reduce noise | 2 | AQ-203-T4, AQ-204-T2 | Hybrid retrieval optimization
3 | AQ-204 | AQ-204-T4 | Validate evidence alignment with question and architecture type | 1 | AQ-204-T3 | Grounded response quality checks
3 | AQ-205 | AQ-205-T1 | Define score-threshold rules for answer quality | 2 | AQ-204-T4 | Response quality baseline
3 | AQ-205 | AQ-205-T2 | Create regression scenarios for common prompt types | 1 | AQ-205-T1 | Reusable evaluation scenarios
3 | AQ-205 | AQ-205-T3 | Compare grounded versus weak-context response quality | 1 | AQ-205-T2 | Comparative retrieval-quality evidence
3 | AQ-205 | AQ-205-T4 | Publish repeatable evaluation checks for future sprints | 1 | AQ-205-T1, AQ-205-T2 | Repeatable validation checklist
4 | AQ-401 | AQ-401-T1 | Define the 9 engineering principles to 3 disciplines mapping model | 2 | AQ-203 | Principle-to-discipline mapping baseline
4 | AQ-401 | AQ-401-T2 | Create targeted context enrichment for People, Process, and Technology | 2 | AQ-401-T1 | Principle-aware prompt enrichment
4 | AQ-401 | AQ-401-T3 | Add principle extraction and request classification for To-Be analysis | 2 | AQ-401-T2 | To-Be routing logic
4 | AQ-401 | AQ-401-T4 | Validate principle coverage for common transformation prompts | 1 | AQ-401-T3 | Coverage validation results
4 | AQ-402 | AQ-402-T1 | Add entity extraction for pillars, roles, and tools from user queries | 2 | AQ-203-T4 | Query entity extraction layer
4 | AQ-402 | AQ-402-T2 | Build multi-hop graph traversal for structural context retrieval | 2 | AQ-402-T1 | Graph traversal retrieval
4 | AQ-402 | AQ-402-T3 | Merge graph and vector context with deduplication and source tagging | 2 | AQ-402-T2, AQ-204-T3 | Hybrid Graph-RAG retriever
4 | AQ-402 | AQ-402-T4 | Add global-summary fallback when no direct entity match exists | 1 | AQ-402-T3 | Fallback retrieval behavior
4 | AQ-403 | AQ-403-T1 | Generate To-Be diagrams in DOT and Mermaid formats from LLM output | 3 | AQ-401, AQ-402 | To-Be diagram generation pipeline
4 | AQ-403 | AQ-403-T2 | Derive PlantUML artifacts from generated architecture outputs | 2 | AQ-403-T1 | PlantUML diagram export
4 | AQ-403 | AQ-403-T3 | Support gap-analysis mode for removed pillars or components | 2 | AQ-403-T1 | Gap-analysis flow
4 | AQ-403 | AQ-403-T4 | Highlight direct and indirect impact nodes in gap diagrams | 2 | AQ-403-T3 | Risk-highlighted gap diagrams
4 | AQ-404 | AQ-404-T1 | Convert long-form LLM analysis into structured document sections | 2 | AQ-401-T3 | Structured narrative content blocks
4 | AQ-404 | AQ-404-T2 | Enable downloadable Word and Excel exports for analysis output | 2 | AQ-404-T1 | Word and Excel export support
4 | AQ-404 | AQ-404-T3 | Enable downloadable PowerPoint and PDF exports for analysis output | 2 | AQ-404-T1 | PowerPoint and PDF export support
4 | AQ-404 | AQ-404-T4 | Validate file naming, MIME types, and preview/download behavior | 1 | AQ-404-T2, AQ-404-T3 | Production-ready export downloads
4 | AQ-405 | AQ-405-T1 | Add persistent chat history for multi-session continuity | 2 | AQ-402 | Session history capability
4 | AQ-405 | AQ-405-T2 | Add token usage tracking and budget visibility in the UI | 2 | AQ-405-T1 | Token usage dashboard
4 | AQ-405 | AQ-405-T3 | Add Langfuse-based observability and trace capture for LLM flows | 2 | AQ-402, AQ-405-T2 | LLM traceability
4 | AQ-405 | AQ-405-T4 | Refine UI experience for upload, mode badges, and download actions | 1 | AQ-404-T4, AQ-405-T1 | Improved user interaction flow